## Event Planning Worksheet
Create professional Gantt charts in GanttPRO in a few clicks
Event Planning Worksheet | [8 empty] | 2023-04-06 10:15
Color | WBS Number |  |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Predecessor | Cost | Actual cost
| 1 | 8 weeks or more prior to the event: |  |  |  | 2023-04-09 10:15 | 2023-04-23 10:15 |  | 0 | 88 | 0 | 0 |  |  |  |  | 0 | 0
| 1.1 |  | Investigate possible dates for the program. |  |  | 2023-04-09 10:15 | 2023-04-09 10:15 |  | 0 | 8 | 0 | 0 |  |  |  |  | 0 | 0
| 1.1.1 |  |  | Check Calendar for all events |  | 2023-04-09 10:15 | 2023-04-09 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 1.2 |  | Reserve the necessary facilities, including rain location. |  |  | 2023-04-10 10:15 | 2023-04-10 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 1.3 |  | Review your budget |  |  | 2023-04-11 10:15 | 2023-04-11 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 1.4 |  | Request a sample contract |  |  | 2023-04-12 10:15 | 2023-04-12 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 1.5 |  | Allocate resources |  |  | 2023-04-13 10:15 | 2023-04-13 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 1.6 |  | Meet with your advisor |  |  | 2023-04-16 10:15 | 2023-04-16 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 1.7 |  | Develop a marketing plan |  |  | 2023-04-17 10:15 | 2023-04-20 10:15 |  | 0 | 32 | 0 | 0 |  |  |  | 1 | 0 | 0
| 1.7.1 |  |  | Collaborative opportunities |  | 2023-04-17 10:15 | 2023-04-17 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 1.7.2 |  |  | Obtain necessary quotes on printing and other services |  | 2023-04-18 10:15 | 2023-04-18 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 1.7.3 |  |  | Design and order printed publicity pieces |  | 2023-04-19 10:15 | 2023-04-19 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 1.7.4 |  |  | Reserve information tables |  | 2023-04-20 10:15 | 2023-04-20 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 1.8 |  | Obtain sample catering menus |  |  | 2023-04-23 10:15 | 2023-04-23 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 2 | 6-8 weeks prior to the event: |  |  |  | 2023-04-23 10:15 | 2023-05-07 10:15 |  | 0 | 88 | 0 | 0 |  |  |  | 1.7 | 0 | 0
| 2.1 |  | Obtain all signed contracts |  |  | 2023-04-23 10:15 | 2023-04-23 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 2.2 |  | Contracts, vendor invoices, etc. |  |  | 2023-04-24 10:15 | 2023-04-24 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 2.3 |  | Order printed publicity (posters, table tents, etc.) |  |  | 2023-04-25 10:15 | 2023-04-25 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 2.4 |  | Order A/V equipment |  |  | 2023-04-26 10:15 | 2023-04-26 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 2.5 |  | Review facility policies regarding programs, noise, food, and special situations |  |  | 2023-04-27 10:15 | 2023-04-27 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 2.6 |  | Regarding special needs |  |  | 2023-04-27 10:15 | 2023-05-04 10:15 |  | 0 | 48 | 0 | 0 |  |  |  |  | 0 | 0
| 2.6.1 |  |  | electrician |  | 2023-04-27 10:15 | 2023-04-27 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 2.6.2 |  |  | security |  | 2023-04-30 10:15 | 2023-04-30 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 2.6.3 |  |  | additional staffing required |  | 2023-05-01 10:15 | 2023-05-01 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 2.6.4 |  |  | rented equipment |  | 2023-05-02 10:15 | 2023-05-02 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 2.6.5 |  |  | grills |  | 2023-05-03 10:15 | 2023-05-03 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 2.6.4 | 0 | 0
| 2.6.6 |  |  | balloons/helium |  | 2023-05-04 10:15 | 2023-05-04 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 2.6.7 |  |  | amplified sound |  | 2023-05-04 10:15 | 2023-05-04 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 2.6.8 |  |  | special staging |  | 2023-05-04 10:15 | 2023-05-04 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 2.7 |  | Order any additional equipment/materials |  |  | 2023-05-07 10:15 | 2023-05-07 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  | 2.6.8 | 0 | 0
| 2.8 |  | Submit event information |  |  | 2023-05-07 10:15 | 2023-05-07 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 2.9 |  | Place order with the caterer |  |  | 2023-05-07 10:15 | 2023-05-07 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 3 | 5-6 weeks prior to the event: |  |  |  | 2023-05-08 10:15 | 2023-05-10 10:15 |  | 0 | 24 | 0 | 0 |  |  |  | 2.9 | 0 | 0
| 3.1 |  | Submit printed publicity for posting |  |  | 2023-05-08 10:15 | 2023-05-08 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 3.2 |  | Submit reservation for table tents, if applicable |  |  | 2023-05-09 10:15 | 2023-05-09 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 3.3 |  | Confirm reservation of information tables |  |  | 2023-05-10 10:15 | 2023-05-10 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 4 | 4 weeks prior to the event |  |  |  | 2023-05-14 10:15 | 2023-05-16 10:15 |  | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0
| 4.1 |  | Review the budget |  |  | 2023-05-14 10:15 | 2023-05-14 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 4.2 |  | Recruit volunteers for all aspects of upcoming event |  |  | 2023-05-15 10:15 | 2023-05-15 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 4.3 |  | Request any necessary checks |  |  | 2023-05-16 10:15 | 2023-05-16 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 5 | 2 weeks prior to the event |  |  |  | 2023-05-16 10:15 | 2023-05-21 10:15 |  | 0 | 32 | 0 | 0 |  |  |  |  | 0 | 0
| 5.1 |  | Discuss any needed changes in room configuration |  |  | 2023-05-16 10:15 | 2023-05-16 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 5.2 |  | Finalize necessary security/staffing arrangements |  |  | 2023-05-17 10:15 | 2023-05-17 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 5.3 |  | Review all necessary confirmations |  |  | 2023-05-18 10:15 | 2023-05-18 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 5.4 |  | Meet with advisor for an update on your progress |  |  | 2023-05-21 10:15 | 2023-05-21 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 5.5 |  | Review any special rules |  |  | 2023-05-21 10:15 | 2023-05-21 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 6 | 1 week prior to the event |  |  |  | 2023-05-22 10:15 | 2023-05-28 10:15 |  | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0
| 6.1 |  | Contact the contractors to confirm all event details |  |  | 2023-05-22 10:15 | 2023-05-22 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 6.2 |  | Determine who is meeting the entertainment/guest |  |  | 2023-05-23 10:15 | 2023-05-23 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 6.3 |  | When, and where Provide maps/directions as needed |  |  | 2023-05-24 10:15 | 2023-05-24 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 6.4 |  | Review all responsibilities |  |  | 2023-05-25 10:15 | 2023-05-25 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 6.5 |  | Make final arrangements |  |  | 2023-05-28 10:15 | 2023-05-28 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 6.6 |  | Make any final catering arrangements |  |  | 2023-05-28 10:15 | 2023-05-28 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 7 | Day before the event |  |  |  | 2023-05-29 10:15 | 2023-05-31 10:15 |  | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0
| 7.1 |  | Pick up vendor(s) check(s) |  |  | 2023-05-29 10:15 | 2023-05-29 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 7.2 |  | Make any final purchases |  |  | 2023-05-30 10:15 | 2023-05-30 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 7.3 |  | Determine who will introduce the entertainment/guest |  |  | 2023-05-31 10:15 | 2023-05-31 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 8 | Day of the event |  |  |  | 2023-06-04 10:15 | 2023-06-08 10:15 |  | 0 | 40 | 0 | 0 |  |  |  |  | 0 | 0
| 8.1 |  | Responsible party to meets with caterer, vendors, speaker, entertainer |  |  | 2023-06-04 10:15 | 2023-06-04 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 8.2 |  | Decorate/prepare room as appropriate |  |  | 2023-06-05 10:15 | 2023-06-05 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 8.3 |  | Don’t forget the check(s) |  |  | 2023-06-06 10:15 | 2023-06-07 10:15 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 8.4 |  | Enjoy the event! |  |  | 2023-06-08 10:15 | 2023-06-08 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 9 | After the event |  |  |  | 2023-06-11 10:15 | 2023-06-13 10:15 |  | 0 | 24 | 0 | 0 |  |  |  | 8.4 | 0 | 0
| 9.1 |  | Clean up the area |  |  | 2023-06-11 10:15 | 2023-06-12 10:15 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 9.2 |  | Facility shutdown |  |  | 2023-06-13 10:15 | 2023-06-13 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 10 | 1-2 days after the event |  |  |  | 2023-06-14 10:15 | 2023-06-20 10:15 |  | 0 | 40 | 0 | 0 |  |  |  | 9.2 | 0 | 0
| 10.1 |  | Complete an event profile |  |  | 2023-06-14 10:15 | 2023-06-14 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 10.2 |  | File notes with the event profile |  |  | 2023-06-14 10:15 | 2023-06-14 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 10.3 |  | Submit any final receipts for payment |  |  | 2023-06-15 10:15 | 2023-06-15 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 10.4 |  | Send thank-you notes to anyone who helped |  |  | 2023-06-18 10:15 | 2023-06-18 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 10.5 |  | Ensure there were no problems |  |  | 2023-06-19 10:15 | 2023-06-19 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
| 10.6 |  | Make sure all contractors/vendors have received payment |  |  | 2023-06-20 10:15 | 2023-06-20 10:15 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0
This document has been created with the help of https://ganttpro.com online service
You are free to use the document for your purposes with no limitations. To edit it, please, create a copy or use https://ganttpro.com